## Doc4
Related Simplification Items | Activities | Phase | Condition | Additional Information | ID
ABAP4TWL - Removal of Transceiver Integration (SI18: AS_ABAP_TRANSCEIVER_INTEGRATION) | Custom Code Adaption | Before or during conversion project | Mandatory | Remove usages of the deleted objects from your custom code. | SI18: AS_ABAP_TRANSCEIVER_INTEGRATION
ABAPTWL - Change of workflow system user and workflow system jobs (SI20: AS_ABAP_WORKFLOW_USER_JOBS) | Technical System Configuration | During conversion project | Mandatory | Adapt your workflow jobs as described in SAP note 2568271. | SI20: AS_ABAP_WORKFLOW_USER_JOBS
ABAPTWL - Cleanup of orphaned objects (SI02: AS_ABAP_CLEANUP) | Custom Code Adaption | Before or during conversion project | Mandatory | Remove usage of obsolete SAP objects from custom code. | SI02: AS_ABAP_CLEANUP
ABAPTWL - Dual Stack not supported (SI06: AS_ABAP_DUAL_STACK) | Landscape Redesign | Before conversion project | Mandatory | Split your dual stack system into separate ABAP and Java instances. | SI06: AS_ABAP_DUAL_STACK
ABAPTWL - SSCR license key procedure is no longer supported (SI03: AS_ABAP_SSCR) | Process Design / Blueprint | Before or during conversion project | Optional | Setup control of development activities as recommended in SAP note 2309060 . | SI03: AS_ABAP_SSCR
ABAPTWL - SSCR license key procedure is no longer supported (SI03: AS_ABAP_SSCR) | User Training | Before or during conversion project | Optional | Educate developers about process changes on controlling development activities. | SI03: AS_ABAP_SSCR
ABAPTWL - VM Container not supported (SI04: AS_ABAP_VMCONTAINER) | Custom Code Adaption | Before or during conversion project | Mandatory | Remove any VMC usage in your custom applications. | SI04: AS_ABAP_VMCONTAINER
S4TWL - ACTIVITY-BASED COSTING (SI3_FIN_CO) | Business Operations | During conversion project | Mandatory |  | SI3_FIN_CO
S4TWL - ACTIVITY-BASED COSTING (SI3_FIN_CO) | Custom Code Adaption | During conversion project | Mandatory |  | SI3_FIN_CO
S4TWL - ACTIVITY-BASED COSTING (SI3_FIN_CO) | User Training | During conversion project | Mandatory | Inform customer about missing functionalities | SI3_FIN_CO
S4TWL - ASSET ACCOUNTING (SI2: FIN_AA) | Business Decision | Before conversion project | Mandatory | Decide about future ledger approach for asset accounting. | SI2: FIN_AA
S4TWL - ASSET ACCOUNTING (SI2: FIN_AA) | Business Operations | During conversion project | Mandatory | Execute year-end and month-end closing activities. | SI2: FIN_AA
S4TWL - ASSET ACCOUNTING (SI2: FIN_AA) | Custom Code Adaption | During conversion project | Mandatory | For required custom code adaption refer to simplification item SI1: FIN_AA and SAP note 2270387. | SI2: FIN_AA
S4TWL - ASSET ACCOUNTING (SI2: FIN_AA) | Customizing / Configuration | During conversion project | Mandatory | Perform customizing and configuration required for preparing the data migration and for the future asset accounting design in SAP S/4HANA. | SI2: FIN_AA
S4TWL - ASSET ACCOUNTING (SI2: FIN_AA) | Data cleanup / archiving | Before conversion project | Optional | Reduce number of asset accounting documents to avoid unnecessary data error corrections and to minimize conversion downtime. | SI2: FIN_AA
S4TWL - ASSET ACCOUNTING (SI2: FIN_AA) | Data correction | Before or during conversion project | Mandatory | Check and correct inconsistent data which is relevant for the conversion. | SI2: FIN_AA
S4TWL - ASSET ACCOUNTING (SI2: FIN_AA) | Data migration | During conversion project | Mandatory | Perform data migration to new SAP S/4HANA data model. | SI2: FIN_AA
S4TWL - ASSET ACCOUNTING (SI2: FIN_AA) | Interface Adaption | During conversion project | Mandatory | Adapt or replace obsolete or changed legacy data transfer methods. | SI2: FIN_AA
S4TWL - ASSET ACCOUNTING (SI2: FIN_AA) | Process Design / Blueprint | Before or during conversion project | Mandatory | Create blueprint for required Asset Accounting configuration in SAP S/4HANA. | SI2: FIN_AA
S4TWL - ASSET ACCOUNTING (SI2: FIN_AA) | User Training | During conversion project | Mandatory | Inform users about changes in Asset Accounting. | SI2: FIN_AA
S4TWL - AVAILABILITY OF TRANSACTIONS IN MM-IM (SI2: Logistics_MM-IM) | Custom Code Adaption | During conversion project | Mandatory | Replace customer coding using the transaction codes MB01, MB02 MB04, MB05, MB0A, MB11, MB1A, MB1B, MB1C, MB31, MBNL, MBRL, MBSF, MBSL and MBSU (e.g. by suing CALL TRANSACTION MBxy) by make use of function module BAPI_GOODSMVT_CREATE | SI2: Logistics_MM-IM
S4TWL - AVAILABILITY OF TRANSACTIONS IN MM-IM (SI2: Logistics_MM-IM) | User Training | During conversion project | Optional |  | SI2: Logistics_MM-IM
S4TWL - Amount Field Length Extension (SI8_FIN_GL) | Custom Code Adaption | During conversion project | Mandatory |  | SI8_FIN_GL
S4TWL - Amount Field Length Extension (SI8_FIN_GL) | Software Upgrade / Maintenance | During conversion project | Conditional | Implementation of SAP Notes might be required in case new functionality should be used | SI8_FIN_GL
S4TWL - Authorization Concept for Supplier Invoice (SI14: PROC_MM_IV_AUTH) | Customizing / Configuration | During conversion project | Mandatory | Users working with supplier invoices, additionally need the authorizations based on M_RECH_BUK | SI14: PROC_MM_IV_AUTH
S4TWL - Authorization Objects in QM (SI9: Logistics_QM) | Data correction | After conversion project | Mandatory | Authorization objects in Quality Management have been changed, follow the steps in SAP Note 2505099 to adjust authorization objects | SI9: Logistics_QM
S4TWL - BI Extractors in SAP S/4HANA (SI18: CT_BW_EXTRACTORS) | Interface Adaption | During conversion project | Mandatory | Adjust or change BI extractors. | SI18: CT_BW_EXTRACTORS
S4TWL - BI Extractors in SAP S/4HANA (SI18: CT_BW_EXTRACTORS) | New developments | During conversion project | Optional | Develope solutions for obsolete BW extractors | SI18: CT_BW_EXTRACTORS
S4TWL - BOM, Routing, Production Version (SI16: Logistics - PLM) | Custom Code Adaption | During conversion project | Mandatory |  | SI16: Logistics - PLM
S4TWL - BOM, Routing, Production Version (SI16: Logistics - PLM) | Data migration | During conversion project | Mandatory | It is recommended to migrate BOMs, for which there is no corresponding routing using report CS_BOM_PRODVER_MIGRATION. It is recommended to migrate BOMs, for which there exist corresponding routings using report CS_BOM_PRODVER_MIGRATION02. | SI16: Logistics - PLM
S4TWL - BOM, Routing, Production Version (SI16: Logistics - PLM) | User Training | Before or during conversion project | Mandatory | Production versions are mandatory in S/4HANA. MRP, planned order creation, and production order creation only find a BOM and routing alternative if a production version is maintained for the BOM and routing alternative. | SI16: Logistics - PLM
S4TWL - Batch History (SI36: Logistics_PP) | Business Decision | Any time | Optional | Functionality available in SAP S/4HANA on-premise edition but not considered as future technology. | SI36: Logistics_PP
S4TWL - Batch Input for Customer Master/Supplier Master (SI25: MasterData_BP) | Custom Code Adaption | Before or during conversion project | Conditional | Adjust your custom code according to the new process. | SI25: MasterData_BP
S4TWL - Batch Input for Customer Master/Supplier Master (SI25: MasterData_BP) | Process Design / Blueprint | Before conversion project | Mandatory | Batch Input to maintain customer master and supplier master data is not supported since SAP S/4 HANA 1809, please use one of the following alternatives: Business Partner SOAP Services. Refer to SAP Note 2472030 for more information IDocs (CREMAS/DEBMAS) Mass Transactions (XK99/XD99) | SI25: MasterData_BP
S4TWL - Batch Input for Customer Master/Supplier Master (SI25: MasterData_BP) | User Training | Before or during conversion project | Mandatory |  | SI25: MasterData_BP
S4TWL - Batch Input for Enterprise Asset Management [EAM] (SI5: Logistics_PM) | Business Decision | Before or during conversion project | Optional | Please check if you use Batch Input for creating / changing Plant Maintenance data. If Yes do not invest further in this kind of technology. Recommendation within EAM is to use the API´s wherever possible | SI5: Logistics_PM
S4TWL - Batch Input for Enterprise Asset Management [EAM] (SI5: Logistics_PM) | Custom Code Adaption | During conversion project | Optional | If you use Batch Input for creating / changing Plant Maintenance data, recommendation within EAM is to use the API´s wherever possible. | SI5: Logistics_PM
S4TWL - Billing Document Output Management (SI14: SD_BILLING_OM) | Business Decision | Before conversion project | Mandatory | Additionally to the existing output management based on NAST a new Output Management solution is adopted S/4 HANA-wide. Thereby a unified solution can be used for all Output Management activities. The existing Output Management solution however is still the default. | SI14: SD_BILLING_OM
S4TWL - Billing Document Output Management (SI14: SD_BILLING_OM) | Custom Code Adaption | During conversion project | Conditional | Replace custom code for previous NAST-based output management. | SI14: SD_BILLING_OM
S4TWL - Billing Document Output Management (SI14: SD_BILLING_OM) | Customizing / Configuration | During conversion project | Conditional | Configure new output management. | SI14: SD_BILLING_OM
S4TWL - Billing Document Output Management (SI14: SD_BILLING_OM) | Landscape Redesign | During or after conversion project | Conditional | If new output management is used, setup required technical infrastructure. | SI14: SD_BILLING_OM
S4TWL - Billing Document Output Management (SI14: SD_BILLING_OM) | Process Design / Blueprint | During or after conversion project | Optional | Additionally to the existing output management based on NAST a new Output Management solution is adopted S/4 HANA-wide. Thereby a unified solution can be used for all Output Management activities. The existing Output Management solution however is still the default. | SI14: SD_BILLING_OM
S4TWL - Billing Document Output Management (SI14: SD_BILLING_OM) | Technical System Configuration | During or after conversion project | Conditional | Configure technical infrastructure for new output management. | SI14: SD_BILLING_OM
S4TWL - Billing Document Output Management (SI14: SD_BILLING_OM) | User Training | After conversion project | Optional |  | SI14: SD_BILLING_OM
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Business Decision | Before conversion project | Mandatory | Before the conversion project you need to make a decision on whether the Business Partner ID and the Customer/Vendor ID should be the same. | SI2: MasterData_BP
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Custom Code Adaption | During conversion project | Mandatory | Adapt your Custom Code as per Note 2265093 "Custom Code Adaption" section | SI2: MasterData_BP
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Customizing / Configuration | Before or during conversion project | Mandatory | Check CVI customizing and trigger necessary changes e.g. missing BP Role Category, Define Number Assignments according to the S/4 Conversion guide chapter Introduce Business Partner Approach (Customer Vendor Integration) (Note 2265093)Check and maintain BP customizing e.g. missing tax types. | SI2: MasterData_BP
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Data correction | During conversion project | Mandatory | Carry out post-implementation steps as per BP_Conversion Document.pdf attached to SAP Note 2211312 The customer/vendor transformation is bidirectional. You can both process customer/vendor master records from business partner maintenance as well as populate data from customer/vendor processing to the business partner. After the successful S/4 conversion process you have to activate the post processing for direction Business Partner a Customer /Vendor. | SI2: MasterData_BP
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Data correction | Before or during conversion project | Conditional | If the Business Function CA_BP_SO is present in your system -> activate it as per Note 2265093In case that the Business Function CA_BP_SOA does not yet exist in the system -> you have to create a new Business Function in the customer namespace with the switches VENDOR_SFWS_SC1 and VENDOR_SFWS_SC2. The new customer specific Business Function must be of type Enterprise Business Function (G) - see also Mandatory checks for customer, vendor and contact as per Note 2265093. | SI2: MasterData_BP
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Data correction | Before or during conversion project | Mandatory | Check master data consistency using CVI_MIGRATION_PRECHK and maintain consistency.Check and clean-up customer/vendor data e.g. missing @-sign in the e-mail address. Run Business Partner Pre-Check PRECHECK_UPGRADATION_REPORT to verify the results according to the Note 2211312. | SI2: MasterData_BP
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Data migration | During conversion project | Conditional | Valid for IS-OIL: In S4HANA all the IS-OIL specific fields (including customer BDRP data fields) have been adapted as per the new Framework of BP. The IS-OIL Fields related to Vendor and Customer now have been moved to BP under the roles FLCU01 (Customer), FLVN01 (Vendor) | SI2: MasterData_BP
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Data migration | Before or during conversion project | Mandatory | Perform Synchronization (Data load) via Synchronization Cockpit (Note 2265093) | SI2: MasterData_BP
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Process Design / Blueprint | Before conversion project | Mandatory | There is a list of transactions that redirect you to the transaction BP, as well as a list of obsolete transactions as per Note 2265093 , adjust your business process accordingly. | SI2: MasterData_BP
S4TWL - Business Partner Approach (SI2: MasterData_BP) | Technical System Configuration | Before or during conversion project | Mandatory | Implement SAP S/4HANA Conversion Pre-Checks according to the SAP S/4HANA Conversion guide chapter Pre-Checks as per Note 2265093 . | SI2: MasterData_BP
S4TWL - Business Partner Approach (SI2: MasterData_BP) | User Training | During conversion project | Optional | User training to use new transactions for Business Partners in S/4HANA | SI2: MasterData_BP
S4TWL - Business User Management (SI21: BUSINESS_USER) | Customizing / Configuration | During conversion project | Mandatory | Configure update channel for workplace address data If HR integration is active, configure and maintain employee master data | SI21: BUSINESS_USER
S4TWL - Business User Management (SI21: BUSINESS_USER) | Data correction | Before or during conversion project | Mandatory | check user data (as part of general business partner introduction) | SI21: BUSINESS_USER
S4TWL - Business User Management (SI21: BUSINESS_USER) | Data migration | During conversion project | Mandatory | If HR integration is active, run HCM business partner synchronization as described in HCM simplification SAP Note 2340095 If HR integration is not active, create or upload person data wiht Fiori app "Maintain employee" | SI21: BUSINESS_USER
S4TWL - Business User Management (SI21: BUSINESS_USER) | Fiori Implementation | During conversion project | Conditional | If HR integration is not active, implement Fiori app "Maintain employee" | SI21: BUSINESS_USER
S4TWL - Business User Management (SI21: BUSINESS_USER) | User Training | During conversion project | Mandatory |  | SI21: BUSINESS_USER
S4TWL - CASH MANAGEMENT - Bank Accounts (SI2_FIN_CM) | Custom Code Adaption | During conversion project | Mandatory | Adopt custom code to fit to the new logic described in note 2870766. | SI2_FIN_CM
S4TWL - CASH MANAGEMENT - Bank Accounts (SI2_FIN_CM) | Customizing / Configuration | During conversion project | Mandatory | Create number ranges, account types, import of bank statements. | SI2_FIN_CM
S4TWL - CASH MANAGEMENT - Bank Accounts (SI2_FIN_CM) | Data migration | During conversion project | Mandatory | Migrate House Banks into Bank Account Management. | SI2_FIN_CM
S4TWL - CASH MANAGEMENT - Bank Accounts (SI2_FIN_CM) | Fiori Implementation | During conversion project | Mandatory | Implement Fiori apps required to manage banks and bank accounts. | SI2_FIN_CM
S4TWL - CASH MANAGEMENT - Bank Accounts (SI2_FIN_CM) | User Training | During conversion project | Mandatory | Inform users about changes to user interface and business logics. | SI2_FIN_CM
S4TWL - CASH MANAGEMENT - GENERAL (SI1_FIN_CM) | Business Decision | During conversion project | Mandatory |  | SI1_FIN_CM
S4TWL - CASH MANAGEMENT - GENERAL (SI1_FIN_CM) | Customizing / Configuration | During conversion project | Mandatory |  | SI1_FIN_CM
S4TWL - CASH MANAGEMENT - GENERAL (SI1_FIN_CM) | Implementation project required | During conversion project | Optional |  | SI1_FIN_CM
S4TWL - COST ELEMENTS (SI7: FIN_CO) | Custom Code Adaption | During conversion project | Mandatory |  | SI7: FIN_CO
S4TWL - COST ELEMENTS (SI7: FIN_CO) | Process Design / Blueprint | During conversion project | Mandatory |  | SI7: FIN_CO
S4TWL - COST ELEMENTS (SI7: FIN_CO) | User Training | During conversion project | Mandatory |  | SI7: FIN_CO
S4TWL - Changed Interfaces (SI15: CT_Integration) | Interface Adaption | During conversion project | Mandatory | Adjust any interfaces that use obsolete RFC. | SI15: CT_Integration
S4TWL - Changes In List Reports For Order and Notification (SI6: Logistics_PM) | Technical System Configuration | During conversion project | Conditional | Implement the SAP Notes 393393 and 551133 if needed and run the reports 'QM_PHASE_FILL' and 'RIAFVC_IPHAS_FILL' before the ugrade to SAP S/4HANA (if not done already). | SI6: Logistics_PM
S4TWL - Changes In List Reports For Order and Notification (SI6: Logistics_PM) | User Training | During conversion project | Conditional | In case you use the transaction IW37, IW49, please use IW37n or IW49n instead. | SI6: Logistics_PM
S4TWL - Classic MM-PUR GUI Transactions replacement (SI11: PROC_MM_DYN) | Custom Code Adaption | During conversion project | Mandatory | Replace custom code refering to old BAPIs | SI11: PROC_MM_DYN
S4TWL - Classic MM-PUR GUI Transactions replacement (SI11: PROC_MM_DYN) | Customizing / Configuration | During conversion project | Optional |  | SI11: PROC_MM_DYN
S4TWL - Classic MM-PUR GUI Transactions replacement (SI11: PROC_MM_DYN) | User Training | During conversion project | Optional |  | SI11: PROC_MM_DYN
S4TWL - Classification - Data Cleanup before Migration (SI32: Logistics_PLM) | Data correction | During conversion project | Mandatory | If any inconsistencies are found in table INOB, fix them as described in SAP Note 2949845. | SI32: Logistics_PLM
S4TWL - Conversion of Employees to Business Partners (SI2: HR_Empl) | Customizing / Configuration | During conversion project | Mandatory | Perform customizing for HCM business partner synchronization and the required business user management. | SI2: HR_Empl
S4TWL - Conversion of Employees to Business Partners (SI2: HR_Empl) | Data cleanup / archiving | During conversion project | Mandatory | Check and correct data and customizing for vendors related to employees. Archive unused vendor and employee data. Check and correct employee master data according to used HCM integration scenario and business partner configuration in ERP system. | SI2: HR_Empl
S4TWL - Conversion of Employees to Business Partners (SI2: HR_Empl) | Data migration | During conversion project | Mandatory | Perform business partner synchronization for employees after technical conversion using SUM. | SI2: HR_Empl
S4TWL - Conversion of Employees to Business Partners (SI2: HR_Empl) | Miscellaneous | Before or during conversion project | Mandatory | As prerequisite for the synchronization of employees and business partners, the customer-vendor integration with business partner has to be activated in the ERP system as described in simplification item SI2: MasterData_BP (SAP note 2265093). | SI2: HR_Empl
S4TWL - Conversion of Employees to Business Partners (SI2: HR_Empl) | Process Design / Blueprint | During conversion project | Conditional | If business downtime is important, do a careful cut over planning for the employee/business partner synchronization and plan for some optional iteration cycles to optimize the synchronization runtime. | SI2: HR_Empl
S4TWL - Conversion to S/4HANA Material Ledger and Actual Costing (SI6: FIN_MISC_ML) | Business Operations | During conversion project | Conditional | If Material ledger is already active => complete step "Post closing" for all ML costing runs created before conversion/upgrade | SI6: FIN_MISC_ML
S4TWL - Conversion to S/4HANA Material Ledger and Actual Costing (SI6: FIN_MISC_ML) | Customizing / Configuration | During conversion project | Conditional | If actual costing is active => customize account determination as of SAP S/4HANA 1610 | SI6: FIN_MISC_ML
S4TWL - Conversion to S/4HANA Material Ledger and Actual Costing (SI6: FIN_MISC_ML) | Customizing / Configuration | During conversion project | Mandatory |  | SI6: FIN_MISC_ML
S4TWL - Conversion to S/4HANA Material Ledger and Actual Costing (SI6: FIN_MISC_ML) | Data cleanup / archiving | Before conversion project | Optional | Archiving historic data | SI6: FIN_MISC_ML
S4TWL - Conversion to S/4HANA Material Ledger and Actual Costing (SI6: FIN_MISC_ML) | Data correction | During conversion project | Mandatory |  | SI6: FIN_MISC_ML
S4TWL - Conversion to S/4HANA Material Ledger and Actual Costing (SI6: FIN_MISC_ML) | Data migration | During conversion project | Mandatory |  | SI6: FIN_MISC_ML
S4TWL - Conversion to S/4HANA Material Ledger and Actual Costing (SI6: FIN_MISC_ML) | Software Upgrade / Maintenance | During conversion project | Mandatory | Implementation of SAP Notes mentioned in SAP Note "2345739" for your corresponding Support Package. | SI6: FIN_MISC_ML
S4TWL - Credit Management (SI1: FIN_MISC_CR) | Business Decision | Before or during conversion project | Mandatory |  | SI1: FIN_MISC_CR
S4TWL - Credit Management (SI1: FIN_MISC_CR) | Business Operations | During conversion project | Mandatory |  | SI1: FIN_MISC_CR
S4TWL - Credit Management (SI1: FIN_MISC_CR) | Custom Code Adaption | During conversion project | Mandatory |  | SI1: FIN_MISC_CR
S4TWL - Credit Management (SI1: FIN_MISC_CR) | Customizing / Configuration | During conversion project | Mandatory |  | SI1: FIN_MISC_CR
S4TWL - Credit Management (SI1: FIN_MISC_CR) | Data correction | During conversion project | Mandatory |  | SI1: FIN_MISC_CR
S4TWL - Credit Management (SI1: FIN_MISC_CR) | Data migration | During conversion project | Mandatory |  | SI1: FIN_MISC_CR
S4TWL - Credit Management (SI1: FIN_MISC_CR) | Interface Adaption | During conversion project | Optional |  | SI1: FIN_MISC_CR
S4TWL - Credit Management (SI1: FIN_MISC_CR) | User Training | During conversion project | Mandatory |  | SI1: FIN_MISC_CR
S4TWL - Credit Management (SI4: SD_CM) | Business Decision | Before or during conversion project | Mandatory |  | SI1: FIN_MISC_CR
S4TWL - Credit Management (SI4: SD_CM) | Business Operations | During conversion project | Mandatory |  | SI1: FIN_MISC_CR
S4TWL - Credit Management (SI4: SD_CM) | Custom Code Adaption | During conversion project | Mandatory |  | SI1: FIN_MISC_CR
S4TWL - Credit Management (SI4: SD_CM) | Customizing / Configuration | During conversion project | Mandatory |  | SI1: FIN_MISC_CR
S4TWL - Credit Management (SI4: SD_CM) | Data correction | During conversion project | Mandatory |  | SI1: FIN_MISC_CR
S4TWL - Credit Management (SI4: SD_CM) | Data migration | During conversion project | Mandatory |  | SI1: FIN_MISC_CR
S4TWL - Credit Management (SI4: SD_CM) | Interface Adaption | During conversion project | Optional |  | SI1: FIN_MISC_CR
S4TWL - Credit Management (SI4: SD_CM) | User Training | During conversion project | Mandatory |  | SI1: FIN_MISC_CR
S4TWL - Currencies in Universal Journal (SI6_FIN_GL) | Business Decision | Before conversion project | Optional |  | SI6_FIN_GL
S4TWL - Currencies in Universal Journal (SI6_FIN_GL) | Customizing / Configuration | During conversion project | Mandatory |  | SI6_FIN_GL
S4TWL - Currencies in Universal Journal (SI6_FIN_GL) | Process Design / Blueprint | During conversion project | Optional |  | SI6_FIN_GL
S4TWL - Currencies in Universal Journal (SI6_FIN_GL) | User Training | During conversion project | Mandatory |  | SI6_FIN_GL
S4TWL - Custom Fields (SI13: CT_Custom-Fields) | Custom Code Adaption | During or after conversion project | Optional | Enable existing CDS extensions to SAP S/4HANA tables for SAP Fiori applications (raised by ATC checks) | SI13: CT_Custom-Fields
S4TWL - Custom Fields (SI13: CT_Custom-Fields) | Customizing / Configuration | During or after conversion project | Optional | Preapre and enable Custom Database Fields Usage in SAP Fiori Applications | SI13: CT_Custom-Fields
S4TWL - DATA MODEL CHANGES IN FIN (SI1_FIN_General) | Custom Code Adaption | During conversion project | Mandatory | Adapt access to the new simplified Finance data model in your customer-specific programs | SI1_FIN_General
S4TWL - DATA MODEL IN INVENTORY MANAGEMENT [MM-IM] (SI1: Logistics_MM-IM) | Business Decision | Before conversion project | Optional | Decide which locking methods to be used for goods movements | SI1: Logistics_MM-IM
S4TWL - DATA MODEL IN INVENTORY MANAGEMENT [MM-IM] (SI1: Logistics_MM-IM) | Custom Code Adaption | During conversion project | Mandatory |  | SI1: Logistics_MM-IM
S4TWL - DATA MODEL IN INVENTORY MANAGEMENT [MM-IM] (SI1: Logistics_MM-IM) | Customizing / Configuration | During or after conversion project | Mandatory |  | SI1: Logistics_MM-IM
S4TWL - DATA MODEL IN INVENTORY MANAGEMENT [MM-IM] (SI1: Logistics_MM-IM) | Customizing / Configuration | During conversion project | Mandatory |  | SI1: Logistics_MM-IM
S4TWL - DATA MODEL IN INVENTORY MANAGEMENT [MM-IM] (SI1: Logistics_MM-IM) | Technical System Configuration | During conversion project | Optional |  | SI1: Logistics_MM-IM
S4TWL - DATA STRUCTURE CHANGES IN ASSET ACCOUNTING (SI1: FIN_AA) | Custom Code Adaption | During conversion project | Mandatory |  | SI1: FIN_AA
S4TWL - DMEE (SI10_FIN_General) | Data migration | Any time | Conditional | If you switch to successor transaction DMEEX, perform migration as described in SAP note 3370503. | SI10_FIN_General
S4TWL - DMEE (SI10_FIN_General) | User Training | Any time | Optional | Inform user about status change and alternative transaction. | SI10_FIN_General
S4TWL - Data Model Changes in SD Pricing (SI2: SD_PRIC) | Custom Code Adaption | During conversion project | Mandatory |  | SI2: SD_PRIC
S4TWL - Data Model Changes in SD Pricing (SI2: SD_PRIC) | Data migration | After conversion project | Mandatory |  | SI2: SD_PRIC
S4TWL - Data Model Changes in SD Pricing (SI2: SD_PRIC) | Technical System Configuration | During conversion project | Conditional | If pricing table KONV has been enhanced with customer-specific fields, you must ensure that the appended fields are also added to the new structure PRCS_ELEMENTS_DATA. | SI2: SD_PRIC
S4TWL - Determination of default values in Intrastat reporting (SI3: FIN_SLL_ISR_DV) | Customizing / Configuration | After conversion project | Mandatory |  | SI3: FIN_SLL_ISR_DV
S4TWL - Determination of default values in Intrastat reporting (SI3: FIN_SLL_ISR_DV) | Data correction | After conversion project | Mandatory |  | SI3: FIN_SLL_ISR_DV
S4TWL - Document Flow Consistency for Goods Receipt to Inbound Delivery (SI12: Logistics_MM-IM) | Customizing / Configuration | Before or during conversion project | Mandatory | Check the current business process for goods receipt processing whether affected or not by the stricter consistency checks applied. Change the business process by ensuring the inbound delivery contains the correct data prior to posting goods receipt, if applicable. | SI12: Logistics_MM-IM
S4TWL - Download Data in MS Access out of List (SI2: Logistics_PM) | Custom Code Adaption | During or after conversion project | Optional | MS Access is not considered as future technology. Functional equivalent is available (Excel / Open Office). | SI2: Logistics_PM
S4TWL - Download Data in MS Access out of List (SI2: Logistics_PM) | User Training | During conversion project | Optional |  | SI2: Logistics_PM
S4TWL - ESS and MSS (SI5: HR_JAVA_ESS_MSS) | Customizing / Configuration | During conversion project | Conditional | If customer uses SAP ERP HCM and Java-based ESS and MSS in one system, then configure WebDynpro ABAP-based ESS and MSS services or SAP Fiori based ESS and MSS apps (mandatory in conditional and prepare phase) | SI5: HR_JAVA_ESS_MSS
S4TWL - ESS and MSS (SI5: HR_JAVA_ESS_MSS) | Software Upgrade / Maintenance | Before or during conversion project | Conditional | If customer uses SAP HCM and Java-based ESS and MSS in one system then remove Netweaver JAVA stack | SI5: HR_JAVA_ESS_MSS
S4TWL - ESS and MSS (SI5: HR_JAVA_ESS_MSS) | User Training | During conversion project | Conditional |  | SI5: HR_JAVA_ESS_MSS
S4TWL - Enterprise Search in EAM (SI8: Logistics) | Customizing / Configuration | During conversion project | Mandatory | You have to activate the Enterprise search models and do the described configuration steps. | SI8: Logistics
S4TWL - Enterprise Search in SAP Product Lifecycle Management [SAP PLM] (SI1: Logistics_PLM) | Custom Code Adaption | During conversion project | Mandatory | Custom code needs to be adjusted to reference to the new model names | SI1: Logistics_PLM
S4TWL - Enterprise Search in SAP Product Lifecycle Management [SAP PLM] (SI1: Logistics_PLM) | Customizing / Configuration | During conversion project | Mandatory | With SAP S/4HANA the Enterprise Search models are now replication free search models (using HANA DB tables instead) within SAP Product Lifecycle Management (SAP PLM). The Enterprise Search models' names have changed and due to this， the related customizing (Define Settings for PLM Search under PLM Search) needs to be adjusted. SAP Note 2212593 | SI1: Logistics_PLM
S4TWL - FIORI APPLICATIONS FOR SUITE ON HANA ON-PREMISE (SI10: CT_FIORI) | Custom Code Adaption | During conversion project | Conditional | if Fiori has been enhanced SAP ERP 6.0, analyze and perform required enhancements in SAP S/4HANA | SI10: CT_FIORI
S4TWL - FIORI APPLICATIONS FOR SUITE ON HANA ON-PREMISE (SI10: CT_FIORI) | Fiori Implementation | During conversion project | Conditional | if Fiori is used in SAP ERP 6.0, configure successor apps | SI10: CT_FIORI
S4TWL - FIORI APPLICATIONS FOR SUITE ON HANA ON-PREMISE (SI10: CT_FIORI) | User Training | During conversion project | Conditional | train users on new Fiori apps | SI10: CT_FIORI
S4TWL - Foreign Trade (SI3: SD_FT) | Business Decision | Before conversion project | Mandatory | In SAP S/4HANA, the Foreign Trade (SD-FT) functionality is not available anymore. Instead, SAP S/4HANA for international trade within SAP S/4HANA is the successor | SI3: SD_FT
S4TWL - Foreign Trade (SI3: SD_FT) | Custom Code Adaption | During conversion project | Mandatory |  | SI3: SD_FT
S4TWL - Foreign Trade (SI3: SD_FT) | Customizing / Configuration | During conversion project | Conditional | If GTS shall be used depending on scope and business decision, configure new GTS processes | SI3: SD_FT
S4TWL - Foreign Trade (SI3: SD_FT) | Data migration | During conversion project | Conditional | If GTS shall be used depending on scope and business decision, migrate data to GTS | SI3: SD_FT
S4TWL - Foreign Trade (SI3: SD_FT) | Interface Adaption | During conversion project | Conditional | If GTS shall be used depending on scope and business decision, provide interface between GTS and S/4HANA | SI3: SD_FT
S4TWL - Foreign Trade (SI3: SD_FT) | Landscape Redesign | During conversion project | Conditional | If GTS shall be used depending on scope and business decision, provide GTS system | SI3: SD_FT
S4TWL - Foreign Trade (SI3: SD_FT) | New developments | During conversion project | Conditional | If GTS shall be used depending on scope and business decision, provide developments for new GTS processes | SI3: SD_FT
S4TWL - Foreign Trade (SI3: SD_FT) | Process Design / Blueprint | Before conversion project | Conditional | If GTS shall be used depending on scope and business decision, design new GTS processes | SI3: SD_FT
S4TWL - Foreign Trade (SI3: SD_FT) | User Training | During or after conversion project | Conditional | If GTS shall be used depending on scope and business decision, train users | SI3: SD_FT
S4TWL - Foreign Trade fields in Material Master (SI6:MasterData_PM) | Business Decision | Before conversion project | Mandatory | In SAP S/4HANA, the Foreign Trade (SD-FT) functionality is not available anymore. Instead, SAP S/4HANA for international trade within SAP S/4HANA is the successor. | SI6:MasterData_PM
S4TWL - Foreign Trade fields in Material Master (SI6:MasterData_PM) | Custom Code Adaption | During conversion project | Mandatory |  | SI6:MasterData_PM
S4TWL - Foreign Trade fields in Material Master (SI6:MasterData_PM) | Customizing / Configuration | During conversion project | Mandatory | To migrate financial documents in Foreign Trade to Trade Finance, you carry out the migration steps available as Customizing activities (transaction SPRO, SAP Reference IMG) under: Conversion of Accounting to SAP S/4HANA-->Preparations and Migration of Customizing-->Preparations for Migration of Financial Documents to Trade Finance Conversion of Accounting to SAP S/4HANA-->Data Migration-->Migration of Financial Documents to Trade Finance Complete Migration of Financial Documents to Trade Finance conversion of Accounting to SAP S/4HANA-->Activities after Migration-->Manual Activities for Trade Finance" | SI6:MasterData_PM
S4TWL - Foreign Trade fields in Material Master (SI6:MasterData_PM) | Customizing / Configuration | Before conversion project | Mandatory |  | SI6:MasterData_PM
S4TWL - Foreign Trade fields in Material Master (SI6:MasterData_PM) | Data cleanup / archiving | During conversion project | Mandatory | You should Run as post conversion activity, report ZUPDATE_MARC_FOREIGN_TRADE(note 2458666) - to delete the content of the obsolete fileds. This avoids accidental side effects. | SI6:MasterData_PM
S4TWL - Foreign Trade fields in Material Master (SI6:MasterData_PM) | Implementation project required | Before conversion project | Mandatory | GTS functionality is considerred as a pre-project, plan time and resources for the new implementation. | SI6:MasterData_PM
S4TWL - Foreign Trade fields in Material Master (SI6:MasterData_PM) | Interface Adaption | Before conversion project | Mandatory |  | SI6:MasterData_PM
S4TWL - Foreign Trade fields in Material Master (SI6:MasterData_PM) | Process Design / Blueprint | Before conversion project | Conditional | In case relevant SAP GTS needs to be installed, analysis of all foreign trade processes that are currently in use is requiered, before conversion. | SI6:MasterData_PM
S4TWL - Foreign Trade fields in Material Master (SI6:MasterData_PM) | User Training | During conversion project | Mandatory |  | SI6:MasterData_PM
S4TWL - Foreign Trade within SAP S/4HANA Procurement (SI15: PROC_FT) | Custom Code Adaption | During conversion project | Mandatory |  | SI15: PROC_FT
S4TWL - Foreign Trade within SAP S/4HANA Procurement (SI15: PROC_FT) | Interface Adaption | During conversion project | Conditional | It is possible that 3rd party foreign trade system will need adjustments by the respective 3rd party Solution/Service Provider. | SI15: PROC_FT
S4TWL - Foreign Trade within SAP S/4HANA Procurement (SI15: PROC_FT) | Landscape Redesign | Before conversion project | Conditional | Foreign trade functionality in S/4HANA is replaced. SAP GTS can be connected to S/4HANA to run the respective foreign trade processes | SI15: PROC_FT
S4TWL - Foreign Trade within SAP S/4HANA Procurement (SI15: PROC_FT) | User Training | During or after conversion project | Mandatory |  | SI15: PROC_FT
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Business Decision | Before conversion project | Optional |  | SI1_FIN_GL
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Custom Code Adaption | During conversion project | Mandatory |  | SI1_FIN_GL
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Customizing / Configuration | During conversion project | Mandatory |  | SI1_FIN_GL
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Customizing / Configuration | During conversion project | Mandatory |  | SI1_FIN_GL
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Data cleanup / archiving | During conversion project | Mandatory |  | SI1_FIN_GL
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Data correction | During conversion project | Mandatory |  | SI1_FIN_GL
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Data migration | During conversion project | Mandatory |  | SI1_FIN_GL
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Fiori Implementation | During conversion project | Optional |  | SI1_FIN_GL
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Implementation project required | Before conversion project | Optional |  | SI1_FIN_GL
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Process Design / Blueprint | During conversion project | Mandatory |  | SI1_FIN_GL
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | Process Design / Blueprint | Before conversion project | Optional |  | SI1_FIN_GL
S4TWL - GENERAL LEDGER (SI1_FIN_GL) | User Training | During conversion project | Mandatory |  | SI1_FIN_GL
S4TWL - Generic Check for SAP S/4HANA Conversion and Upgrade (SI22: GENERIC_CHECKS) | Custom Code Adaption | Before or during conversion project | Mandatory | This simplification Item serves as an anchor for assigning custom code check related content, which is not related to any specific functional or technical area (e.g. deletion of unused orphaned objects). | SI22: GENERIC_CHECKS
S4TWL - Generic Check for SAP S/4HANA Conversion and Upgrade (SI22: GENERIC_CHECKS) | Miscellaneous | Before or during conversion project | Mandatory | This simplification item provides various generic, technical checks which need to run before a conversion or upgrade in SAP S/4HANA and which affect all customers - irrespective of the specific SAP S/4HANA target release. | SI22: GENERIC_CHECKS
S4TWL - Globalization – Financials (SI1_GSFIN) | Custom Code Adaption | During conversion project | Mandatory |  | SI1_GSFIN
S4TWL - Globalization – Financials (SI1_GSFIN) | Interface Adaption | During conversion project | Mandatory |  | SI1_GSFIN
S4TWL - Globalization – Financials (SI1_GSFIN) | User Training | During conversion project | Mandatory |  | SI1_GSFIN
S4TWL - Globalization – Logistics (SI1_GSLOG) | Custom Code Adaption | During conversion project | Optional |  | SI1_GSLOG
S4TWL - Globalization – Logistics (SI1_GSLOG) | Process Design / Blueprint | Before or during conversion project | Mandatory | SAP recommends using the following: •SAP Tax Declaration Framework for Fiscal and Accounting Legal Reporting. •TAXBRA tax procedure for the tax calculation. Note: SAP Tax Declaration Framework is part of the Compatible Add-ons and requires an additional license. | SI1_GSLOG
S4TWL - Globalization – Logistics (SI1_GSLOG) | User Training | During conversion project | Mandatory |  | SI1_GSLOG
S4TWL - Goods movements without exclusive locking by material valuation (SI7: Logistics_MM-IM) | Business Decision | Before conversion project | Mandatory |  | SI7: Logistics_MM-IM
S4TWL - Goods movements without exclusive locking by material valuation (SI7: Logistics_MM-IM) | Customizing / Configuration | During conversion project | Conditional | Set up locking method | SI7: Logistics_MM-IM
S4TWL - Graphical display of available quantity in MRP evaluations (SI39: Logisticis_PP) | Fiori Implementation | Before or after conversion project | Optional | Encourage users to switch to the Monitor or Check Material Coverage apps to use the graphical evaluations. | SI39: Logisticis_PP
S4TWL - Graphical display of available quantity in MRP evaluations (SI39: Logisticis_PP) | User Training | Before conversion project | Optional | Graphical evaluation of the Stock/Requirements list is still available within the apps Monitor or Check Material Coverage. Encourage users to switch to these new apps for graphical evaluations. | SI39: Logisticis_PP
S4TWL - ITS services in QM (SI_2_Logistics_QM) | Custom Code Adaption | During conversion project | Mandatory |  | SI_2_Logistics_QM
S4TWL - ITS services in QM (SI_2_Logistics_QM) | Customizing / Configuration | During conversion project | Conditional | In case WebDynpro applications will be used as replacement, then PFCG role for NWBC Quality Inspector (SAP_SR_QUALITY_INSPECT_5) need to be configured, and respective authorizations | SI_2_Logistics_QM
S4TWL - ITS services in QM (SI_2_Logistics_QM) | Technical System Configuration | During conversion project | Mandatory | ITS services in QM - Internet Application Components (IAC) in QM are not available within SAP S/4HANA, As alternatives, you could use the corresponding QM transactions in SAP GUI for HTML or you could use the WebDynpro applications mentioned below, which are part of the PFCG role for NWBC Quality Inspector (SAP_SR_QUALITY_INSPECT_5). | SI_2_Logistics_QM
S4TWL - ITS services in QM (SI_2_Logistics_QM) | User Training | During conversion project | Mandatory |  | SI_2_Logistics_QM
S4TWL - JOB SCHEDULING (SI8:CROSS_BC_CCM-BTC) | Business Operations | During conversion project | Mandatory | Execute report BTCTRNS2 of SNOTE 2499529 | SI8:CROSS_BC_CCM-BTC
S4TWL - JOB SCHEDULING (SI8:CROSS_BC_CCM-BTC) | Software Upgrade / Maintenance | During conversion project | Optional | Implement SAP Notes to prevent automatic execution of new job scheduling. | SI8:CROSS_BC_CCM-BTC
S4TWL - JOB SCHEDULING (SI8:CROSS_BC_CCM-BTC) | Software Upgrade / Maintenance | During conversion project | Optional | Implement SAP Notes to prevent automatic execution of new job scheduling. | SI8:CROSS_BC_CCM-BTC
S4TWL - JOB SCHEDULING (SI8:CROSS_BC_CCM-BTC) | Technical System Configuration | During conversion project | Optional | Decide if new job scheduling shall be used and adjust parameterization | SI8:CROSS_BC_CCM-BTC
S4TWL - LEGACY SYSTEM MIGRATION WORKBENCH (SI9: CT_LSMW) | Business Decision | Before conversion project | Optional | The use of LSMW is restricted for migrations to SAP S/4HANA. The use of LSMW for data load to SAP S/4HANA is not recommended and at the customer's own risk. SAP recommends using SAP S/4HANA Migration Cockpit and Migration Object Modeler instead of LSMW. | SI9: CT_LSMW
S4TWL - LEGACY SYSTEM MIGRATION WORKBENCH (SI9: CT_LSMW) | Interface Adaption | During conversion project | Conditional | If you still plan to use LSMW, provide customer specific adjustments or workarounds for restrictions on certain Batch Input or Direct Input programs. | SI9: CT_LSMW
S4TWL - Logistics Batch Management (S14: MasterData) | User Training | During conversion project | Mandatory | "Following transaction codes are now obsolete: MSC1, MSC2, MSC3 and MSC4. The functional equivalent in SAP S/4HANA, starting on-premise edition 1511 are the following transactions:MSC1N, MSC2N, MSC3N, MSC4N. Instruct users on the usage of the new Transaction codes" | S14: MasterData
S4TWL - MDM Catalog (SI7: PROC_MDM ) | Custom Code Adaption | During or after conversion project | Optional |  | SI7: PROC_MDM
S4TWL - MDM Catalog (SI7: PROC_MDM ) | Customizing / Configuration | Before or after conversion project | Mandatory | SAP S/4HANA Self-Service Procurement must be used instead of the SAP SRM MDM catalog. | SI7: PROC_MDM
S4TWL - MDM Catalog (SI7: PROC_MDM ) | Data migration | During or after conversion project | Conditional | Set up a business user for SAP S/4HANA Self-Service Procurement. | SI7: PROC_MDM
S4TWL - MDM Catalog (SI7: PROC_MDM ) | Interface Adaption | Before or after conversion project | Conditional | Content needs to be imported into S/4HANA via OCI5 | SI7: PROC_MDM
S4TWL - MDM Catalog (SI7: PROC_MDM ) | Process Design / Blueprint | Before conversion project | Mandatory | The SAP SRM catalog MDM is not available in SAP S/4HANA. It's replaced by the catalog search function as part of SAP S/4HANA Self-Service Procurement. | SI7: PROC_MDM
S4TWL - MDM Catalog (SI7: PROC_MDM ) | User Training | After conversion project | Optional |  | SI7: PROC_MDM
S4TWL - MRP fields in Material Master (SI7:MasterData_PM) | Business Operations | After conversion project | Conditional | If the scheduling margin key is not specified, then you should run the conversion of planned orders into production orders every day. If Scheduling Margin Key is defined in t-code OMSR, it is mandatory to maintain it, see section Scheduling Margin Key . | SI7:MasterData_PM
S4TWL - MRP fields in Material Master (SI7:MasterData_PM) | User Training | Before or during conversion project | Mandatory | Train changes on material and article master transactions | SI7:MasterData_PM
S4TWL - Material Ledger Obligatory for Material Valuation (SI3: Logistics_MM-IM) | Business Operations | During conversion project | Mandatory |  | SI3: Logistics_MM-IM
S4TWL - Material Ledger Obligatory for Material Valuation (SI3: Logistics_MM-IM) | Custom Code Adaption | During conversion project | Mandatory |  | SI3: Logistics_MM-IM
S4TWL - Material Ledger Obligatory for Material Valuation (SI3: Logistics_MM-IM) | Data correction | During conversion project | Mandatory |  | SI3: Logistics_MM-IM
S4TWL - Material Ledger Obligatory for Material Valuation (SI3: Logistics_MM-IM) | Data migration | During conversion project | Mandatory |  | SI3: Logistics_MM-IM
S4TWL - Material Ledger Obligatory for Material Valuation (SI3: Logistics_MM-IM) | User Training | During or after conversion project | Optional |  | SI3: Logistics_MM-IM
S4TWL - Material Number Field Length Extension (SI4: MasterData_PM) | Custom Code Adaption | During conversion project | Mandatory | Custom Code related information See SAP Note: 2215424, 2215852 | SI4: MasterData_PM
S4TWL - Material Number Field Length Extension (SI4: MasterData_PM) | Data migration | During conversion project | Conditional | The Long Material Number within the DIMP Add-On (Discrete Industries & Mill Products) Although the industry solution DIMP is part of SAP S/4HANA, the already existing DIMP LAMA-functionality for a long material number (LAMA) will not be part of SAP S/4HANA. In S/4HANA the material number is natively extended to 40 characters. Special conversion steps are needed to migrate the existing DIMP LAMA solution to the new S/4HANA extended material number. For further information on the conversion of the DIMP LAMA-functionality and the DIMP Manufacturer Parts Number to S/4HANA please check notes 2270396 and 2270836. | SI4: MasterData_PM
S4TWL - Material Number Field Length Extension (SI4: MasterData_PM) | Data migration | During conversion project | Mandatory | ALE change pointer entries related to master data distribution (see SAP Help: LINK) have to be processed completely before the conversion to SAP S/4HANA. Changes recorded before the conversion will no longer be available compatibly after the conversion to SAP S/4HANA. | SI4: MasterData_PM
S4TWL - Material Number Field Length Extension (SI4: MasterData_PM) | Miscellaneous | Before conversion project | Optional | Conversion Pre-Checks related to Material Number Field Length Extension It´s recommended to execute conversion pre-check (for details see SAP Note: 2216958). For the conversion of selection variants see SAP Note 1696821 for details. Note that code adaptions will be needed even if you decide not to activate the extended material number functionality and stay with 18 characters | SI4: MasterData_PM
S4TWL - Material Number Field Length Extension (SI4: MasterData_PM) | Process Design / Blueprint | Before or during conversion project | Mandatory | The default setting, both after the conversion to SAP S/4HANA and for new installations, is that the extended material number functionality is NOT activated. To use a material number with 40 characters, you need to activate this functionality as described in SAP note 2267140 . | SI4: MasterData_PM
S4TWL - Material Number Field Length Extension (SI4: MasterData_PM) | User Training | During conversion project | Optional | Use of new Material Number Field Length | SI4: MasterData_PM
S4TWL - Material Valuation - Statistical moving average price (SI4: Logistics_MM-IM) | Business Decision | Before or during conversion project | Optional | Decide to deactive statistical moving average price. It is optional in SAP S/4HANA if you convert from SAP ERP, however, it is recommended to achieve a significant increase of transactional data throughput for goods movements. It is important to note that the deactivation is not reversible. | SI4: Logistics_MM-IM
S4TWL - Material Valuation - Statistical moving average price (SI4: Logistics_MM-IM) | Custom Code Adaption | During conversion project | Conditional | If you decide to deactivate statistical moving average price, adjust your own coding respectively. | SI4: Logistics_MM-IM
S4TWL - Material Valuation - Statistical moving average price (SI4: Logistics_MM-IM) | Customizing / Configuration | During conversion project | Conditional | The report SAPRCKM_NO_EXCLUSIVELY_LOCKING can be used to deactivate the statistical moving average price. | SI4: Logistics_MM-IM
S4TWL - New Customizing for Exchange Rate Difference Handling (SI21: PROC_MM_IV_ERD) | Custom Code Adaption | During conversion project | Mandatory |  | SI21: PROC_MM_IV_ERD
S4TWL - New Default Security Settings for SAP S/4HANA (SI27: CT_SECURE_BY_DEFAULT) | Business Operations | During or after conversion project | Conditional | After the conversion or upgrade, check if you need to configure log retention for the different logs (e.g. SAP S/4HANA Security Audit Log, SAP S/4HANA Table Logging, SAP HANA Audit Log) to control the size of the different logs. | SI27: CT_SECURE_BY_DEFAULT
S4TWL - New Default Security Settings for SAP S/4HANA (SI27: CT_SECURE_BY_DEFAULT) | Customizing / Configuration | During conversion project | Conditional | In case you accept the new security settings to be applied during conversion, check if you need to extend roles with additional authorizations for calling specific function modules (only from SAP S/4HANA 2020 onwards) and for calling WebDynpro applications (only from SAP S/4HANA 2021 onwards). | SI27: CT_SECURE_BY_DEFAULT
S4TWL - New Default Security Settings for SAP S/4HANA (SI27: CT_SECURE_BY_DEFAULT) | Technical System Configuration | During conversion project | Mandatory | Decide if you want to take over the new security settings during conversion or if you want to opt out (not recommended). | SI27: CT_SECURE_BY_DEFAULT
S4TWL - New Default Security Settings for SAP S/4HANA (SI27: CT_SECURE_BY_DEFAULT) | User Training | During conversion project | Conditional | In case you accept the new security settings to be applied during conversion, educate your administrators on the changes. | SI27: CT_SECURE_BY_DEFAULT
S4TWL - New advanced ATP in SAP S/4HANA – Table VBBS (SI1: Logistics_ATP) | Custom Code Adaption | During conversion project | Mandatory | If you have custom code calling table VBBS, create a db view on table VBBE, and use that view instead of the table VBBS. SAP Note: 2209696 | SI1: Logistics_ATP
S4TWL - New advanced ATP in SAP S/4HANA – Table VBBS (SI1: Logistics_ATP) | Data migration | During conversion project | Mandatory | Manual step only for SAP S/4HANA 1511 and SAP S/4HANA 1610, For SAP S/4HANA 1709 and newer, the necessary actions are automated and executed in SUM phase using identifying name ATP_XPRA_SUITE_TO_S4_V2. SAP Note: 2209696 | SI1: Logistics_ATP
S4TWL - OUTPUT MANAGEMENT (SI4: CT_OM) | Business Decision | Before conversion project | Optional | Decide if new output management or NAST-based output shall be used. | SI4: CT_OM
S4TWL - OUTPUT MANAGEMENT (SI4: CT_OM) | Custom Code Adaption | During conversion project | Conditional | Replace custom code for previous NAST based output management | SI4: CT_OM
S4TWL - OUTPUT MANAGEMENT (SI4: CT_OM) | Customizing / Configuration | During conversion project | Conditional | Configure new output management. | SI4: CT_OM
S4TWL - OUTPUT MANAGEMENT (SI4: CT_OM) | Landscape Redesign | After conversion project | Conditional | If new output management is used, setup required technical infrastructure | SI4: CT_OM
S4TWL - OUTPUT MANAGEMENT (SI4: CT_OM) | Process Design / Blueprint | During or after conversion project | Conditional | Additionally to the existing output management based on NAST a new Output Management solution is adopted S/4 HANA-wide. Thereby a unified solution can be used for all Output Management activities. The existing Output Management solution however still can be activated. | SI4: CT_OM
S4TWL - OUTPUT MANAGEMENT (SI4: CT_OM) | Technical System Configuration | After conversion project | Conditional | Configure technical infrastructure for new output management | SI4: CT_OM
S4TWL - OUTPUT MANAGEMENT (SI4: CT_OM) | User Training | After conversion project | Optional |  | SI4: CT_OM
S4TWL - Object List Number Field Length Extension (SI10: Logistics_PM) | Custom Code Adaption | During conversion project | Mandatory | If Objectlists are used in custom code it has to be ensured that new field length can be processed | SI10: Logistics_PM
S4TWL - Output Management Adoption in Purchase Order (SI9: PROC_MM_OUTPUT) | Business Decision | Before conversion project | Mandatory | Additionally to the existing output management based on NAST a new Output Management solution is adopted S/4 HANA-wide. Thereby a unified solution can be used for all Output Management activities. The existing Output Management solution however still can be activated. | SI9: PROC_MM_OUTPUT
S4TWL - Output Management Adoption in Purchase Order (SI9: PROC_MM_OUTPUT) | Custom Code Adaption | During conversion project | Conditional | Replace custom code for previous NAST-based output management. | SI9: PROC_MM_OUTPUT
S4TWL - Output Management Adoption in Purchase Order (SI9: PROC_MM_OUTPUT) | Customizing / Configuration | During conversion project | Conditional | Configure new output management. | SI9: PROC_MM_OUTPUT
S4TWL - Output Management Adoption in Purchase Order (SI9: PROC_MM_OUTPUT) | Landscape Redesign | After conversion project | Conditional | If new output management is used, setup required technical infrastructure | SI9: PROC_MM_OUTPUT
S4TWL - Output Management Adoption in Purchase Order (SI9: PROC_MM_OUTPUT) | Process Design / Blueprint | During or after conversion project | Conditional | Additionally to the existing output management based on NAST a new Output Management solution is adopted S/4 HANA-wide. Thereby a unified solution can be used for all Output Management activities. The existing Output Management solution however still can be activated. | SI9: PROC_MM_OUTPUT
S4TWL - Output Management Adoption in Purchase Order (SI9: PROC_MM_OUTPUT) | Technical System Configuration | After conversion project | Conditional | Configure technical infrastructure for new output management | SI9: PROC_MM_OUTPUT
S4TWL - Output Management Adoption in Purchase Order (SI9: PROC_MM_OUTPUT) | User Training | After conversion project | Optional |  | SI9: PROC_MM_OUTPUT
S4TWL - PP-MRP - Subcontracting (SI1: Logistics_PP-MRP) | Custom Code Adaption | During conversion project | Mandatory |  | SI1: Logistics_PP-MRP
S4TWL - PP-MRP - Subcontracting (SI1: Logistics_PP-MRP) | Customizing / Configuration | Before or during conversion project | Mandatory |  | SI1: Logistics_PP-MRP
S4TWL - PP-MRP - Subcontracting (SI1: Logistics_PP-MRP) | Data cleanup / archiving | During conversion project | Mandatory | Create MRP areas for every subcontractor | SI1: Logistics_PP-MRP
S4TWL - PROFIT AND LOSS PLANNING AND PROFIT CENTER PLANNING (SI2_FIN_CO) | Business Decision | Before or during conversion project | Optional | Decide on planning platform - old planning functionalities or SAP BPC for S/4HANA Finance | SI2_FIN_CO
S4TWL - PROFIT AND LOSS PLANNING AND PROFIT CENTER PLANNING (SI2_FIN_CO) | Customizing / Configuration | During conversion project | Conditional | If going forward ERP planning functions still used, restore previous transactions if necessary | SI2_FIN_CO
S4TWL - PROFIT AND LOSS PLANNING AND PROFIT CENTER PLANNING (SI2_FIN_CO) | Customizing / Configuration | During or after conversion project | Conditional | If SAP BPC for S/4HANA Finance is used configure SAP BPC for S/4HANA Finance | SI2_FIN_CO
S4TWL - PROFIT AND LOSS PLANNING AND PROFIT CENTER PLANNING (SI2_FIN_CO) | Interface Adaption | During or after conversion project | Conditional | If SAP BPC for S/4HANA Finance is used set up and adjust interfaces for SAP BPC for S/4HANA Finance | SI2_FIN_CO
S4TWL - PROFIT AND LOSS PLANNING AND PROFIT CENTER PLANNING (SI2_FIN_CO) | Landscape Redesign | During or after conversion project | Conditional | If SAP BPC for S/4HANA Finance is used setup required front end components | SI2_FIN_CO
S4TWL - PROFIT AND LOSS PLANNING AND PROFIT CENTER PLANNING (SI2_FIN_CO) | New developments | During or after conversion project | Conditional | If going forward SAP BPC for S/4HANA Finance is used develop enhancements | SI2_FIN_CO
S4TWL - PROFIT AND LOSS PLANNING AND PROFIT CENTER PLANNING (SI2_FIN_CO) | Process Design / Blueprint | During or after conversion project | Conditional | If SAP BPC for S/4HANA Finance is used design SAP BPC for S/4HANA Finance | SI2_FIN_CO
S4TWL - PROFIT AND LOSS PLANNING AND PROFIT CENTER PLANNING (SI2_FIN_CO) | User Training | During or after conversion project | Conditional | If going forward SAP BPC for S/4HANA Finance is used train users on SAP BPC for S/4HANA Finance | SI2_FIN_CO
S4TWL - Planning File (SI12: Logistics_PP) | Custom Code Adaption | During conversion project | Conditional | If exist, related custom code has to be adjusted. See SAP Note 2227059 | SI12: Logistics_PP
S4TWL - Planning File (SI12: Logistics_PP) | Data migration | During conversion project | Mandatory | After the system conversion, you should run report PPH_SETUP_MRPRECORDS to populate the new planning file table with operative MRP records (PP-MRP) and the report PPH_SETUP_MRPRECORDS_SIMU for simulative MRP records (PP-MP-LTP). Alternatively, you can also use the conversion reports PPH_CONVERT_MRPRECORDS and PPH_CONVERT_MRPRECORDS_SIMU. | SI12: Logistics_PP
S4TWL - Planning Horizon (SI35: Logistics_PP) | Custom Code Adaption | During conversion project | Conditional | Customers can build their own planning application using the BAPI BAPI_MATERIAL_PLANNING. The BAPI has got the same planning parameter options as the classical planning transactions. In that context the processing key NETPL cannot be used any more. | SI35: Logistics_PP
S4TWL - Planning Horizon (SI35: Logistics_PP) | Data cleanup / archiving | During conversion project | Mandatory | If there are still variants for the planning run batch Transactions having the processing key filled with NETPL, these variants have to be deleted. | SI35: Logistics_PP
S4TWL - Pricing Data Model Simplification (SI8: PROC_MM_PRICING) | Custom Code Adaption | During conversion project | Mandatory |  | SI8: PROC_MM_PRICING
S4TWL - Pricing Data Model Simplification (SI8: PROC_MM_PRICING) | Data migration | After conversion project | Mandatory |  | SI8: PROC_MM_PRICING
S4TWL - Pricing Data Model Simplification (SI8: PROC_MM_PRICING) | Technical System Configuration | During conversion project | Mandatory |  | SI8: PROC_MM_PRICING
S4TWL - Profitability Analysis (SI9: FIN_CO) | Business Decision | Before conversion project | Optional |  | SI9: FIN_CO
S4TWL - Profitability Analysis (SI9: FIN_CO) | Customizing / Configuration | During conversion project | Mandatory |  | SI9: FIN_CO
S4TWL - Profitability Analysis (SI9: FIN_CO) | Implementation project required | Before conversion project | Optional |  | SI9: FIN_CO
S4TWL - Profitability Analysis (SI9: FIN_CO) | User Training | During or after conversion project | Optional |  | SI9: FIN_CO
S4TWL - Profitability Segment Number Change of Type (SI15: FIN_CO) | Custom Code Adaption | Before conversion project | Conditional | Adapt usages of PAOBJR found by ATC as described in SAP note <note number>- | SI15: FIN_CO
S4TWL - Project System ITS Services (SI17 Logistics_PS) | Process Design / Blueprint | Before or during conversion project | Mandatory | Selected ITS services for document search, confirmations and creation of claims are not available as of SAP S/4HANA | SI17 Logistics_PS
S4TWL - Project System ITS Services (SI17 Logistics_PS) | User Training | During conversion project | Optional |  | SI17 Logistics_PS
S4TWL - REPLACED TRANSACTION CODES AND PROGRAMS IN FIN (SI2_FIN_General) | Custom Code Adaption | During conversion project | Mandatory | Adjust or replace custom code refering to obsolete transactions | SI2_FIN_General
S4TWL - REPLACED TRANSACTION CODES AND PROGRAMS IN FIN (SI2_FIN_General) | Customizing / Configuration | During conversion project | Optional | For certain replacements conifguratios need to be done | SI2_FIN_General
S4TWL - REPLACED TRANSACTION CODES AND PROGRAMS IN FIN (SI2_FIN_General) | User Training | During conversion project | Mandatory |  | SI2_FIN_General
S4TWL - Rate and Rough-Cut Planning (SI34: Logistics_PP) | Custom Code Adaption | Before or during conversion project | Optional |  | SI34: Logistics_PP
S4TWL - Rate and Rough-Cut Planning (SI34: Logistics_PP) | Customizing / Configuration | Before or during conversion project | Conditional | Based on in-memory computing features of S/4HANA and resulting performance improvement, planning on different levels of aggregation is not necessary furthermore. Hence, Production Versions with BOMs and routings presents the central scheduling level for short-term planning and long-term planning for S/4HANA PP and PPDS. Moreover, using one central scheduling level will simplify reporting and enhaces possibilities of Embedded Analytics. Please, refer to SAP Note 2270240 for more information. Copy any rate routings from scheduling level "Rate-based planning" to scheduling level "Detailed planning" if the production process is modelled by a rate routing and if the routing is only defined for scheduling level "Rate-based planning". | SI34: Logistics_PP
S4TWL - Rate and Rough-Cut Planning (SI34: Logistics_PP) | User Training | Before or during conversion project | Optional |  | SI34: Logistics_PP
S4TWL - Redundant Transactions in QM (SI7: Logistics_QM) | Custom Code Adaption | During conversion project | Conditional | Adapt your Custom Code with regard to unavailable transactions as per SAP Note 2338215 | SI7: Logistics_QM
S4TWL - Redundant Transactions in QM (SI7: Logistics_QM) | Process Design / Blueprint | Before conversion project | Mandatory | A number of QM transactions have been replaced by Fiori apps, other transactions or retired, you need to redesign your process with regard to this | SI7: Logistics_QM
S4TWL - Redundant Transactions in QM (SI7: Logistics_QM) | User Training | During or after conversion project | Mandatory |  | SI7: Logistics_QM
S4TWL - Removal of D/C Indicator from Editing Options (SI9_FIN_GL) | User Training | During conversion project | Mandatory | Educate your users about this change in UI behaviour. | SI9_FIN_GL
S4TWL - Removal of Gender Domain Fixed Values (SI27: MasterData_BP) | Business Process Redesign | During conversion project | Mandatory | Ensure that your business processes (also in connected systems) are prepared to handle the new gender codes properly. | SI27: MasterData_BP
S4TWL - Removal of Gender Domain Fixed Values (SI27: MasterData_BP) | Custom Code Adaption | During conversion project | Mandatory | Usages of fixed values of domains AD_SEX, BU_SEXID and SEXKZ needs to be replaced with values from check tables TSAD15 and TB995. Refer to SAP Note 2928897 for details. | SI27: MasterData_BP
S4TWL - Removed Navigation to Transactions for Evaluations in QM (SI8: Logistics_QM) | Business Operations | After conversion project | Mandatory |  | SI8: Logistics_QM
S4TWL - Reporting/Analytics in Controlling (SI8: FIN_CO) | Business Decision | Before or during conversion project | Mandatory | Decision on the relevant Fiori apps to be used for reporting and planning using embeeded BPC or to reactivate old transactions | SI8: FIN_CO
S4TWL - Reporting/Analytics in Controlling (SI8: FIN_CO) | Custom Code Adaption | During or after conversion project | Mandatory |  | SI8: FIN_CO
S4TWL - Reporting/Analytics in Controlling (SI8: FIN_CO) | Customizing / Configuration | During conversion project | Conditional | If you want to reactivate, act according to steps mentioned in this simplification item | SI8: FIN_CO
S4TWL - Reporting/Analytics in Controlling (SI8: FIN_CO) | Customizing / Configuration | Before or during conversion project | Mandatory |  | SI8: FIN_CO
S4TWL - Reporting/Analytics in Controlling (SI8: FIN_CO) | Fiori Implementation | During conversion project | Conditional | In case you want use Fiori tiles => choose them and configure them | SI8: FIN_CO
S4TWL - Reporting/Analytics in Controlling (SI8: FIN_CO) | User Training | During conversion project | Conditional |  | SI8: FIN_CO
S4TWL - Retail Information System (SI33: Logistics_General) | Custom Code Adaption | During conversion project | Optional | Custom Code adjustments will be requried in case ABAP objects of packets WRB or WRBA are used in custom code. | SI33: Logistics_General
S4TWL - Retail Information System (SI33: Logistics_General) | Process Design / Blueprint | Before or during conversion project | Mandatory | Bluprint for covering reporting requriements using CDS views or SAP BW for reporting requriements that were being fulfilled by RIS functionality. | SI33: Logistics_General
S4TWL - Retail Information System (SI33: Logistics_General) | User Training | During conversion project | Mandatory | Provide user training for the reports based on CDS views or SAP BW instead of RIS. | SI33: Logistics_General
S4TWL - SAP Graphics in EAM Transactions (SI9: Logistics_PM) | Business Decision | Before or during conversion project | Conditional | The graphical output in Enterprise Asset Management transactions using SAP Business Graphics, e.g. in transaction IP19, is not available in SAP S/4HANA. If you are using this graphic output today, you can consider to use use the tabular display options. | SI9: Logistics_PM
S4TWL - SAP Graphics in EAM Transactions (SI9: Logistics_PM) | User Training | During conversion project | Conditional | Use the tabular display options instead of graphic output. | SI9: Logistics_PM
S4TWL - SAP HANA LIVE REPORTING (SI4_FIN_GL) | Custom Code Adaption | During conversion project | Mandatory | If the customer copied calc views delivered by SAP or created user-defined calc views, check and remove if required | SI4_FIN_GL
S4TWL - SAP HANA LIVE REPORTING (SI4_FIN_GL) | New developments | During conversion project | Mandatory | rebuild all existing reporting scenarios with CDS Views | SI4_FIN_GL
S4TWL - SD Simplified Data Models (SI1: SD_GENERAL) | Custom Code Adaption | During conversion project | Mandatory |  | SI1: SD_GENERAL
S4TWL - Scheduling of Maintenance Plan (SI3: Logistics_PM) | Customizing / Configuration | During conversion project | Mandatory | Review your background Jobs which you most probably have scheduled periodically for transaction IP30 (Reports RISTRA20) and create new background jobs for IP30H (Report RISTRA20H). | SI3: Logistics_PM
S4TWL - Side Panel functionality in SAP S/4HANA [on-premise] (SI14: CT_SIDE_PANELS) | Fiori Implementation | During or after conversion project | Optional | if obsolete side-panel CHIPS were used, consider Fiori apps as replacement | SI14: CT_SIDE_PANELS
S4TWL - Side Panel functionality in SAP S/4HANA [on-premise] (SI14: CT_SIDE_PANELS) | User Training | During or after conversion project | Optional | train users on new Fiori apps | SI14: CT_SIDE_PANELS
S4TWL - Simplification of copy/reference handling (SI5: MasterData_PM) | Custom Code Adaption | During conversion project | Mandatory |  | SI5: MasterData_PM
S4TWL - Simplification of copy/reference handling (SI5: MasterData_PM) | Data migration | During conversion project | Mandatory |  | SI5: MasterData_PM
S4TWL - Simplified Product Master Tables Related to OMSR Transaction (SI3: MasterData_PM) | Customizing / Configuration | During conversion project | Conditional | Configuration necessary, if field selection settings within SAP name space exists | SI3: MasterData_PM
S4TWL - Simplified Sourcing (SI7: Logistics_PP) | Custom Code Adaption | During conversion project | Conditional | SAP Note: 2226333 If you implemented BADI MD_MODIFY_SOURCE in SAP ERP, you should check if the intended functionality still works. Also check the changes related to the Simplification Item 2.1.11.11MRP in HANA. | SI7: Logistics_PP
S4TWL - Simplified Sourcing (SI7: Logistics_PP) | Data migration | During conversion project | Mandatory | Actions required for manufactured materials: Check if production versions exist for those BOMs and routings that should be considered by MRP. Report CS_BOM_PRODVER_MIGRATION02 can be used to analyze the situation as well as to create proposals for production versions based on BOM validities. Run the report and accept or reject the proposed production versions. SAP Note 2655077 contains report CS_BOM_PRODVER_MIGRATION02. | SI7: Logistics_PP
S4TWL - Simplified Sourcing (SI7: Logistics_PP) | Data migration | During conversion project | Mandatory | Actions required for externally procured materials, analyse your source list entries No action is required if source list entries refer to contracts and delivery schedules. S/4HANA sourcing finds contracts and delivery schedules without source list entries. Activate the automatic sourcing indicator in the corresponding purchasing info record if the source list entry only refers to a supplier and if the supplier shall be selectable by MRP | SI7: Logistics_PP
S4TWL - Simplified Sourcing (SI7: Logistics_PP) | User Training | During conversion project | Optional | Use new simplified sourcing | SI7: Logistics_PP
S4TWL - Specification Workbench Adjustments (SI14: Logistics_PSS) | User Training | Before or during conversion project | Optional |  | SI14: Logistics_PSS
S4TWL - Storage Location MRP (SI2: Logistics_PP-MRP) | Custom Code Adaption | During conversion project | Conditional | If exist, Custom Code must be adjusted accordingly SAP Note: 2227579 | SI2: Logistics_PP-MRP
S4TWL - Storage Location MRP (SI2: Logistics_PP-MRP) | Data cleanup / archiving | Before or during conversion project | Mandatory |  | SI2: Logistics_PP-MRP
S4TWL - Storage Location MRP (SI2: Logistics_PP-MRP) | Data migration | Before or during conversion project | Mandatory | Run report MRP_AREA_STORAGE_LOC_MIGRATION, Follow the instructions provided by the report. If all prerequisites are fulfilled, then the report generates material master records for planning on MRP area level using the storage location material records. SAP Note: 2216528 | SI2: Logistics_PP-MRP
S4TWL - Summarization Hierarchies in Controlling (SI11: FIN_CO) | User Training | During conversion project | Mandatory |  | SI11: FIN_CO
S4TWL - Supplier Invoice New Archiving (SI20: PROC_MM_IV_ILM) | Business Decision | Before conversion project | Mandatory | Supplier Invoice Archiving does not fully support ILM Integration (with upgade to 1809 ILM Integration is fully supported) | SI20: PROC_MM_IV_ILM
S4TWL - Supplier Invoice New Archiving (SI20: PROC_MM_IV_ILM) | Custom Code Adaption | During conversion project | Mandatory | Implement new BAdIs as indicated in SAP Note 2578291. | SI20: PROC_MM_IV_ILM
S4TWL - Supplier Invoice New Archiving (SI20: PROC_MM_IV_ILM) | Process Design / Blueprint | Before or during conversion project | Mandatory | Adapt the process due to changes in functionality | SI20: PROC_MM_IV_ILM
S4TWL - TECHNICAL CHANGES IN CONTROLLING (SI1: FIN_CO) | Custom Code Adaption | During or after conversion project | Mandatory |  | SI1: FIN_CO
S4TWL - Variant Configuration (SI13: Logistics - PLM) | Custom Code Adaption | During conversion project | Mandatory | Any customer code creating 'Actions' and 'Classification as Selection Condition must be adapted. | SI13: Logistics - PLM
S4TWL - Variant Configuration (SI13: Logistics - PLM) | Data migration | Any time | Optional | New 'Actions' and 'Classification as Selection Condition' can not be created, existing one can still work, but should be corrected using other variant configuration means. | SI13: Logistics - PLM
S4TWL - Webdynpro Applications for Purchase Requisition Transfer from ERP to SRM (SI19: PROC_CPPR_SPPR) | User Training | During or after conversion project | Optional |  | SI19: PROC_CPPR_SPPR
S4TWL - Webshops by Internet Sales or Web Channel Experience Management (SI11: SD_IS) | Business Decision | Before conversion project | Mandatory | The functionalities SAP Internet Sales, SAP E-Commerce, SAP Web Channel, and SAP Web Channel Experience Management in SD are not supported in SAP S/4HANA and have been replaced by SAP Commerce in SAP S/4HANA 1610. | SI11: SD_IS
S4TWL - Webshops by Internet Sales or Web Channel Experience Management (SI11: SD_IS) | Custom Code Adaption | Before or during conversion project | Conditional | Remove the usages of SAP objects in customer objects for which the custom code check refers to note 2225107 as they will not work anymore | SI11: SD_IS
S4TWL - Webshops by Internet Sales or Web Channel Experience Management (SI11: SD_IS) | Process Design / Blueprint | Before or during conversion project | Mandatory | See SAP Note 2271161 for the list of unavailable transactions and functionalities. Replacement functionality is SAP Commerce in SAP S/4HANA 1610. | SI11: SD_IS
S4TWL - Webshops by Internet Sales or Web Channel Experience Management (SI11: SD_IS) | User Training | Before or during conversion project | Mandatory |  | SI11: SD_IS
S4TWL - cDesk (SI6: Logistics_PLM) | Implementation project required | Before or during conversion project | Mandatory | Customers can move to SAP Engineering Control Center for SAP S/4HANA. For more information on upgrading from CAD Desktop to SAP Engineering Control Center, see SAP Note 2117843 or SAP SCN Wiki (URL: https://wiki.scn.sap.com/wiki/x/gQrXHQ). | SI6: Logistics_PLM
S4TWL - cDesk (SI6: Logistics_PLM) | User Training | Before or during conversion project | Mandatory |  | SI6: Logistics_PLM
S4TWL -Miscellaneous minor functionalities in SD Area (SI16: SD_Miscellaneous minor deprecations in SD Area) | Custom Code Adaption | During conversion project | Mandatory |  | SI16: SD_Miscellaneous minor deprecations in SD Area
S4TWL -Miscellaneous minor functionalities in SD Area (SI16: SD_Miscellaneous minor deprecations in SD Area) | Interface Adaption | During conversion project | Mandatory |  | SI16: SD_Miscellaneous minor deprecations in SD Area
S4TWL -Miscellaneous minor functionalities in SD Area (SI16: SD_Miscellaneous minor deprecations in SD Area) | User Training | During conversion project | Optional |  | SI16: SD_Miscellaneous minor deprecations in SD Area
S4TWL – Flexible Benefits not supported in ESS technologies (SI31: Flex_Benefits_not supported_in_ESS) | Business Decision | Before conversion project | Mandatory | Check usage and plan for a customer specific alternative solution, if required. | SI31: Flex_Benefits_not supported_in_ESS
S4TWL – HCM Obsolete Packages (SI19: HR_Obsolete_Packages) | Business Decision | Any time | Mandatory | Decide on and plan for the migration to SAP HCM for SAP S/4HANA, considering the functional implications described in the Business Impact Note of this Simplification Item. | SI19: HR_Obsolete_Packages
S4TWL – Landing Pages and Suite Page Builder (SI18: HR_Landing_Pages_and_Suite_Page_Builder) | Business Decision | Before conversion project | Mandatory | Before the conversion or upgrade to SAP HCM for SAP S/4HANA 2022 or higher, check whether the functionality is used or not. If the functionality is used and still required, a similar function is provided with the Fiori role for HR Specialist | SI18: HR_Landing_Pages_and_Suite_Page_Builder
S4TWL – Landing Pages and Suite Page Builder (SI18: HR_Landing_Pages_and_Suite_Page_Builder) | Fiori Implementation | During or after conversion project | Mandatory | Implement Fiori role for HR Specialist. The new role follows the latest UX strategy from SAP by using an SAP Fiori role instead of HR Renewal Landing Pages based on the Suite Page Builder. Please note: the Web Dynpro ABAP services to maintain employee related data are still supported and will be incorporated into the new HR Specialist role. | SI18: HR_Landing_Pages_and_Suite_Page_Builder
S4TWL – Migration from account solution to ledger solution (SI4_FIN_General) | Business Decision | Before conversion project | Mandatory | Decide about future parallel accounting strategy. | SI4_FIN_General